## Sheet1
Date | Time (minutes) | Task
2011-10-31 | 30 | Meeting with Michelle
2011-10-31 | 180 | Researching image slider and homepage layout
2011-11-01 | 120 | Hompage layout; Edit images for image slider
2011-11-02 | 120 | Add location to homepage; Finish homepage layout; deploy v2011.11.02
2011-11-02 | 30 | Updated "serving families" image; Moved toolbar down; Updated slider image descriptions; Updated locations hyperlink
2011-11-03 | 90 | Worked on the locations page; Deploy v2011.11.03.1
2011-11-03 | 180 | Rename css files; Move header and menu to JavaScript file; Started philosophy, drop shadow for float right pictures and styling
2011-11-04 | 90 | Worked on Philosophy; Curriculum; Rates; Contact Us. Released v2011.11.04.1
840
840